## Project Budget
Budget: Project Plant Pals Operations & Training
[7 empty] | TARGET BUDGET | ACTUAL/ FINAL SPEND | UNDER/ OVER
[7 empty] | 62000 | 0 | 62000
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE DETAILS | HOURS | RATE | UNITS | $/UNIT
Milestone 1: Establish a plant delivery and logistics plan
Task 1: Comprar camiones de reparto | n/a |  |  | 2 | 15000 |  | 30000 |  | -30000
Task 2: Adquirir materiales de embalaje | n/a |  |  | 1500 | 2 |  | 3000 |  | -3000
Task 3: Pagar conductores de reparto | Conductores (2 empleados) | 160 | 15 |  |  |  | 2400 |  | -2400
-- | [5 empty] | Total | 35400 | 0
Milestone 2:
Task 1: Seleccionar proveedor de software y equipos | Proveedor de software |  |  |  |  | 15000 | 15000 |  | -15000
-- | [5 empty] | Total | 15000 | 0
Milestone 3:
Task 1: Desarrollar sesiones de formación | Especialista en RR.HH. | 80 | 50 |  |  |  | 4000 |  | -4000
Task 2: Capacitar empleados | Gerente de Capacitación | 80 | 25 |  |  |  | 2000 |  | -2000
Task 3: Supervisar y mejorar procesos | Gerente de Capacitación | 80 | 25 |  |  |  | 2000 |  | -2000
-- | [5 empty] | Total | 8000 | 0
Reserve buffer | [6 empty] | 3600
TOTAL | [6 empty] | 62000 | 0