## Status Report
Project Name: Plant Pals Operations
Today's date: July 5
Summary |  |  |  | Overall Status (RAG)
We have installed new software to keep track of incoming orders and begun sending out the first test batch of Plant Pals to customers. However, we have run into issues with product quality, customer communication, and the delivery process. Our next milestones include sending the test batch customers newsletters on plant upkeep and sending out the second batch of plants. This report also includes top risks and issues that have arisen and how we intend to take action. |  |  |  | Amber
Completed Tasks and Milestones
Description | Date | Status | Owner |  | Comments
Purchased and installed new software to track incoming orders | June 15 | Completed | IT Specialist |  | The installation took three more days than expected.
Began sending test batches of Plant Pals orders to customers | June 21 | Completed | Compliance Director |  | The number of orders exceeded targets by 15%.
Upcoming Tasks and Milestones
Description | Date | Status | Owner |  | Comments
Send the first batch customers e-newsletters on how to take care of their plants. | July 7 | Upcoming | Marketing Specialist |  | The newsletter must follow Office Green’s brand design guidelines.
Ensure at least 95% on-time delivery rate | July 19 | Upcoming | Fulfillment Director |  | Error rate should be less than 5%.
Top Risks and Issues
Issue |  | Impact | Action |  |  | Owner
10% of plants were not potted correctly |  | Profit loss, complaints, and budget issues | Evaluate and adjust the potting process |  |  | Warehouse Operations Manager
The customer relations team is receiving only 30% of requests and complaints |  | Customer dissatisfaction | Fix problems with new customer service software |  |  | IT Specialist
Insufficient delivery drivers to meet demand |  | Late deliveries and subscription cancellations | Hire and train more delivery drivers |  |  | HR Specialist